## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 |  | Choose the data file with at least 2 crypto currencies (either web scrape the csv file or download to use as csv) | MUST HAVE |  | Anand Kumar Mandal | 3- Completed
1 | 1 |  | Store the data in the database. | MUST HAVE |  | Anand Kumar Mandal | 3- Completed
1 | 1 |  | Calculate the metrics for the data and store in the data frame. | MUST HAVE | 1 | Anand Kumar Mandal | 3- Completed
1 | 1 |  | Apply parallel tasks concepts to the above steps. | MUST HAVE | 1 | Anand Kumar Mandal | 3- Completed
2 | 2 |  | Assign weights for the portfolio. Check if weights are assigned based on the rule (mentioned in 1st september slide). Calculate portfolio return. Calculate portfolio risk. | MUST HAVE |  | Anand Kumar Mandal | 3- Completed
2 | 2 |  | Create two tables for portfolio and portfolio_assets to store currencies,weights,return, metrics. Store and Fetch the data. | SHOULD HAVE | 2 | Anand Kumar Mandal | 3- Completed
2 | 2 |  | Parallel Execution : Extend logic: run multiple rule tests in parallel (ThreadPool). Example: Run equal-weight, risk-based, performance-based at same time. Save outputs into DB. | MUST HAVE | 2 | Anand Kumar Mandal | 3- Completed
2 | 2 |  | Compare portfolio return vs. single assest return with some sample data . Plot the graphs, Draw some insights. Export to csv | MUST HAVE | 2 | Anand Kumar Mandal | 3- Completed
2 | 2 |  | Prepare a .md file which should contain the milestone 2 work that you have done so far. | MUST HAVE |  | Anand Kumar Mandal | 3- Completed
3 | 3 |  | Implement 6 rules to identify risk ( in sep 13th slide) , Store them in the database , Send email alert if anyone rules fails. | MUST HAVE |  | Anand Kumar Mandal | 3- Completed
3 | 3 |  | Predict both portfolio and individual returns using linear regression model. | COULD HAVE | 3 | Anand Kumar Mandal | 3- Completed
4 | 4 |  | Implement rules setter (anyone from sep 30 slide) and calculate portfolio returns, store in Database. | MUST HAVE | 3 | Anand Kumar Mandal | 3- Completed
4 | 4 |  | Apply stress test and see how portfolio returns behave | MUST HAVE |  | Anand Kumar Mandal | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | 1 | Collect/download crypto data (BTC, ETH) as CSV | 2025-08-18 | 2025-08-18 | Anand Kumar Mandal | Build | 3- Completed | 1
US2 | 2 | store CSV into SqLite DB (btc_prices,eth_prices) | 2025-08-19 | 2025-08-19 | Anand Kumar Mandal | Coding | 3- Completed | 1
US3 | 3 | Implement metrics functions (percent change, moving, volatility, signals) | 2025-08-22 | 2025-08-23 | Anand Kumar Mandal | Coding | 3- Completed | 2
US3 | 4 | store matrics into DB (crypto_metrics) | 2025-08-25 | 2025-08-25 | Anand Kumar Mandal | Coding | 3- Completed | 2
US3 | 5 | Validate stored metrics with test cases | 2025-08-26 | 2025-08-26 | Anand Kumar Mandal | Coding | 3- Completed | 1
US4 | 6 | Implement parallel execution (ThreasPoolExecutor) | 2025-08-27 | 2025-08-27 | Anand Kumar Mandal | Unit Test | 3- Completed
Others

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 13th Aug | understanding the project and guidelines to take careof along with date time module | Read from the slides about guidenlines andimplemented datetime module
1 | 14th Aug | Milestone 1 discussion along with SQLite understanding | SQLite implemented with CRUD commands
1 | 18th Aug | Crypto terminologies and raw csv handling of chosen asset to track | Understood crypto terminologies from slides and chose BTC to track
1 | 19th Aug | CSV handling with pandas | Pandas implemented in code editor
1 | 20th Aug | Parallel tasking using concurrent.futures | Learned and implemented parallel tasking using thread pool
1 | 21th Aug | Understanding the numpy | Perfomed various numPy operations
1 | 22th Aug | Different Math calculation like percent_change,volatility on the asset | Applied different math operations for the crypto asset like volatility and percent change
1 | 25th Aug | Storing the metrics in DB | Stored the math operations values (metrics) in DB
1 | 28th Aug | Sprint evalution | feedback taken and improved
1 | 29th Aug | Sprint evalution | _
1 | 30th Aug | Introduction to milestone 2 | _
2 | 1st Sep | Learning about different weight allocation rule | Implemented 3 weight rule from 5
2 | 2nd Sep | Apply weight rule and calculate portfolio return and risk and store it in db | 3 weight rule applied on data stored in DB and portfolio return and risk calculated
2 | 3rd Sep | Continue with the task on sep, 2nd | Improved the selection of 3 rules and again did the calculation
2 | 4th Sep | Apply parallel exceution to calculate different weight rule at same time | Applied paralled execution to calculate weights using the rules for each at same time
2 | 8th Sep | compare the portfolio return vs single asset return and plot the graph for it | compared and plotted a line graph for portfolio vs all 3 asset for all dada
2 | 9tth Sep | pprint evaulation and create a .md me which contains the documentation about milestone 2 | feedback taken and improved on graph with plotting only 15 days to show clear insights
2 | 10th Sep | Sprint evaluation | continued with improvement and creation of .md files
2 | 12th Sep | Sprint evaluation | _
3 | 15th Sep | Understanding about how to send email alert | Implement the email sending using SMTP server
3 | 16th Sep | Different Risk rule discussion | Learned about 6 risks
3 | 17th Sep | continue with the task on sep, 15th | Implemented sharpe and beta rule with advised threshold
3 | 18th Sep | Predict both portfolio and individual return using linear regression model | Linear regression implemented with feature selection having linear depenedency with assets
3 | 20th Sep | Agile documentation explained | went through all the documents provided by mentor
3 | 23th Sep | Sprint evaluation | advised on model accuracy
3 | 24th Sep | Sprint evaluation | model accuracy improved
3 | 26th Sep | Sprint evaluation | _
4 | 30th Sep | Understanding investment spreading rules | implemented one rule( sharpe maximization rule)for weight allocation
4 | 1st Oct | Understanding how to apply stress test and check how portfolio behaves | applied stress test for sample data and checked whether the portfolio behaves with the market or not
4 | 3rd Oct | Sprint evaluation | Little change in stress test to simulate better
4 | 4th Oct | Sprint evaluation | _
4 | 6th Oct | Mock Presentation | Better the presentation by explaining the project and not to deep with the terminologies

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-13 | 2025-08-29 | Anand Kumar Mandal | Use minimum 2 assests | _ | Metrics calculation aligned | clarified with mentor, implemented with minimum 2 assests
2 | Sprint 1 | 2025-08-13 | 2025-08-29 | Anand Kumar Mandal | Review metric calculation logic | _ | continue with current calculation methods | teviewed metrics calculation and aligned with mentor feedback
3 | Sprint 2 | 2025-09-01 | 2025-09-12 | Anand Kumar Mandal | Use 3 assests for portfolio return weights | _ | continue portfolio optimization | implemented as advised
4 | Sprint 2 | 2025-09-01 | 2025-09-12 | Anand Kumar Mandal | Apply weight capping rules | Unclear rules previously | continue using weight rules | claarified with mentor, capped weights at 50%
5 | Sprint 2 | 2025-09-01 | 2025-09-12 | Anand Kumar Mandal | Plot one portfolio return vs asset | Multiple plots | continue plotting return | implemented as advised
6 | Sprint 3 | 2025-09-15 | 2025-09-26 | Anand Kumar Mandal | Build linear dependency for regression model | Missing linear dependency | continue performance improvment | checked which features have linear dependency in predictingthe returns
7 | Sprint 3 | 2025-09-15 | 2025-09-26 | Anand Kumar Mandal | Improve features that with prediction for individual assets | features that dont contribute in prediction | portfolio returns and USDC values predicted well | used KBest feature selection and standard scalar
8 | Sprint 4 | 2025-09-30 | 2025-10-04 | Anand Kumar Mandal | use any investment spreasing rule | Equal weight rule | Any other rule | checked in thee slides for 30th sept to implement other rule
9 | Sprint 4 | 2025-09-30 | 2025-10-04 | Anand Kumar Mandal | aApply stress test | _ | simulate the portfolio return in different scenarious of market | tested the portfolio return for weight using rule on sampled data for diff erent scenarious of market