## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anand Kumar Mandal | 2025-08-27 | Choose the data file with at Least 2 crypto currencies and store in db-I used irrelevant table names | 1 | Anand Kumar Mandal | Maintainability | Changed the table names to common ones | 2025-08-27 | Closed | I do this mistake everywhere as I use some name for execution at the momemt-Now I am aware of it
2 | Anand Kumar Mandal | 2025-09-08 | In visualization.I dint add the graph for risk comparison | 2 | Anand Kumar Mandal | User Interface | Added it and derived insights from it | 2025-09-09 | Closed | Understood when to visualize what.
2 | Anand Kumar Mandal | 2025-09-02 | The choosen dataset was not good for my operations or calculations | 2 | Anand Kumar Mandal | Logical | I found a perfect dataset with multiple coins | 2025-09-02 | Closed | It washard finding the good dataset,but I`m now aware of how to choose datasets based on the specific
3 | Anand Kumar Mandal | 2025-09-24 | Was adviced to add regularization techniques to avoid overfitting | 3 | Anand Kumar Mandal | Standards | The task was done | 2025-09-25 | Closed | Made me understand the importance of producing a clean work.
4 | Anand Kumar Mandal | 2025-10-01 | Was adviced allocate weights dynamically to the coins | 4 | Anand Kumar Mandal | Logical | The task was done | 2025-10-02 | CLosed | I understood the use of doing it.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others